## Blad1
Project Fifa
Groep 10: EA-Sports-3-0
Groepslid: Noël van Bijnen
Datum |  |  | Tijd | Plaats | Verrichte werkzaamheden | Afspraken en opmerkingen
2017-04-18 | Week 1 | di |  | School | Organiseren van Github. | Iedereen heeft tijd besteed aan met het gebruiken van Github.
| Week 1 |  |  | School | bereijkbaarheidslijst gemaakt.
| Week 1 |  |  | School | whatsapp groep aangemaakt.
| Week 1 |  |  | school | logboek begonnen en aangepast.
2017-04-19 | Week 1 | wo |  | School | PvA Planning aangemaakt.
| Week 1 |  |  | School | 2de interview gehouden.
2017-04-20 | Week 1 | do |  | School | planning afgemaakt en compleet.
| Week 1 |  |  | School | technisch ontwerp.
| Week 1 |  |  | School | functioneel ontwerp.
2017-04-21 | Week 1 | vr |  | School | wireframe site gemaakt.
| Week 1 |  |  | School
| Week 1 |  |  | School
2017-05-01 | Week 2 | ma |  | School | wireframe site gemaakt.
| Week 2 |  |  | School | wireframes c# app gemaakt.
2017-05-02 | Week 2 | di |  | School | wireframes site gemaakt.
| Week 2 |  |  | School | wireframes c# app gemaakt.
2017-05-03 | Week 2 | wo |  | School | wireframe site gemaakt.
| Week 2 |  |  | School | C# app gewerkt
2017-05-04 | Week 2 | do |  | School | wireframe site gemaakt.
| Week 2 |  |  | School | C# app gewerkt
2017-05-08 | Week 3 | ma |  | School | C# app gewerkt
| Week 3 |  |  | School
2017-05-09 | Week 3 | di |  | School | C# app gewerkt
| Week 3 |  |  | School
2017-05-10 | Week 3 | wo |  | School | C# app gewerkt
| Week 3 |  |  | School
2017-05-11 | Week 3 | do |  | School | C# app gewerkt
| Week 3 |  |  | School
2017-05-12 | Week 3 | vr |  | School | C# app gewerkt
| Week 3 |  |  | School
2017-05-08 | Week 4 | ma |  | School | C# app gewerkt
| Week 4 |  |  | School
2017-05-09 | Week 4 | di |  | School | C# app gewerkt
| Week 4 |  |  | School
2017-05-10 | Week 4 | wo |  | School | C# app gewerkt
| Week 4 |  |  | School
2017-05-11 | Week 4 | do |  | School
| Week 4 |  |  | School
2017-05-12 | Week 4 | vr |  | School
| Week 4 |  |  | School